## Cover
Sweet Shop
Requirements Traceability Matrix
Document Version: | 1.0
Status: | Draft for Review
Date: | April 2026
Application URL: | https://sweetshop.netlify.app
Reference: | Product Specification v2.0
Derives from: | Test Strategy v1.0 + Test Plan v1.0 + Test Cases v3.0
Purpose
This Requirements Traceability Matrix (RTM) provides bidirectional traceability between every documented requirement (FR-01 to FR-18 and NFR-01 to NFR-08) from the Product Specification v2.0 and the test cases that verify it. It is the single auditable artifact that proves no requirement is left untested and no test case is orphaned from a documented requirement.
Sheets in this Workbook
Sheet | Description
1. Cover | This sheet — purpose, version, sheet index
2. RTM (Forward) | Requirement → Test Cases. The classic forward traceability view. Every FR/NFR mapped to its test cases with execution status.
3. RTM (Reverse) | Test Case → Requirements. Reverse traceability — proves no orphan test cases.
4. Coverage Summary | Counts and percentages: requirements covered, cases per priority, automation breakdown, status dashboard.
5. Test Case Master | Full list of all 158 test cases with their attributes, used as the data source by the other sheets.
6. Defect Anchor | Empty placeholder sheet for defect IDs raised against requirements during execution. Populated as defects are logged.
7. Execution Log | Per-case execution status entry sheet — testers update Pass/Fail/Blocked here during the cycle.
8. Legend | Definitions for priority, automation tag, status values.

## RTM (Forward)
Req ID | Type | Category | Requirement | Spec Reference | Test Scenario | Test Case IDs | TC Count | P0 | P1 | P2 | P3 | Executed | Passed | Failed | Blocked | Coverage Status | Defects (count)
FR-01 | Functional | Product Browsing | Users shall be able to view all 16 products on the Browse Sweets page | Spec §11.1, §4.2 | Browse Sweets — Catalogue Rendering | TC-020, TC-021, TC-022, TC-023, TC-024, TC-025, TC-026 | 7 | 1 |  | 2 | 4 | 0 | 0 | 0 | 0 | Covered | 0
FR-02 | Functional | Product Browsing | Each product shall display image, name, description, price, Add to Basket button | Spec §11.1, §4.2 | Product Card Structure | TC-021, TC-022, TC-024, TC-025, TC-026 | 5 | 1 |  | 1 | 3 | 0 | 0 | 0 | 0 | Covered | 0
FR-03 | Functional | Product Browsing | The homepage shall display a curated Most Popular section of 4 products | Spec §11.1, §4.1 | Home — Most Popular Section | TC-010, TC-011, TC-012, TC-013 | 4 |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Covered | 0
FR-04 | Functional | Basket / Cart | Users shall be able to add products from both Home and Browse Sweets pages | Spec §11.2, §4.2.4 | Add to Basket — Multi-source | TC-030, TC-031, TC-033, TC-034, TC-035, TC-036, TC-037, TC-038 | 8 | 3 | 1 | 4 |  | 0 | 0 | 0 | 0 | Covered | 0
FR-05 | Functional | Basket / Cart | The basket item count in the navbar shall update in real-time | Spec §11.2, §3.1 | Navbar Basket Counter | TC-007, TC-008, TC-030, TC-031, TC-032, TC-034, TC-050, TC-217 | 8 | 5 | 1 |  | 2 | 0 | 0 | 0 | 0 | Covered | 0
FR-06 | Functional | Basket / Cart | Users shall be able to empty the basket via Empty Basket control | Spec §11.2, §4.3.4 | Empty Basket Flow | TC-050, TC-051, TC-078, TC-094, TC-169 | 5 |  | 1 | 1 | 3 | 0 | 0 | 0 | 0 | Covered | 0
FR-07 | Functional | Basket / Cart | Users shall be able to select a delivery method (Collect or Standard Shipping) | Spec §11.2, §4.3.3 | Delivery Selection | TC-060, TC-061, TC-062, TC-063, TC-064, TC-091 | 6 | 1 | 2 | 3 |  | 0 | 0 | 0 | 0 | Covered | 0
FR-08 | Functional | Basket / Cart | Users shall be able to enter and attempt to redeem a promotional code | Spec §11.2, §4.3.4 | Promo Code Redemption | TC-070, TC-071, TC-072, TC-073, TC-074, TC-075, TC-076, TC-077, TC-078, TC-079 | 10 |  | 2 | 3 | 5 | 0 | 0 | 0 | 0 | Covered | 0
FR-09 | Functional | Basket / Cart | The basket shall display the current item list and count dynamically | Spec §11.2, §4.3.2 | Basket Display & Subtotal | TC-041, TC-042, TC-043, TC-044, TC-045, TC-080, TC-081, TC-082, TC-083, TC-084, TC-086, TC-087, TC-088, TC-091, TC-092, TC-093, TC-094, TC-095, TC-096 | 19 | 8 | 4 | 6 | 1 | 0 | 0 | 0 | 0 | Covered | 0
FR-10 | Functional | Basket / Cart | The order total shall update dynamically when delivery option changes | Spec §11.2, §5.7 | Order Total Recalculation | TC-043, TC-061, TC-062, TC-079, TC-080, TC-081, TC-083, TC-085, TC-089, TC-090, TC-095, TC-096 | 12 | 5 | 5 | 2 |  | 0 | 0 | 0 | 0 | Covered | 0
FR-11 | Functional | Checkout | Users shall fill in a billing address form with field-level validation | Spec §11.3, §4.3.5 | Billing Form Validation | TC-110, TC-111, TC-112, TC-113, TC-114, TC-115, TC-116, TC-117, TC-118, TC-119, TC-120, TC-121, TC-122, TC-123 | 14 | 1 | 8 | 5 |  | 0 | 0 | 0 | 0 | Covered | 0
FR-12 | Functional | Checkout | Users shall fill in a payment details form with field-level validation | Spec §11.3, §4.3.6 | Payment Form Validation | TC-130, TC-131, TC-132, TC-133, TC-134, TC-135, TC-136, TC-137, TC-138 | 9 |  | 5 | 3 | 1 | 0 | 0 | 0 | 0 | Covered | 0
FR-13 | Functional | Checkout | Continue to checkout shall trigger full form validation | Spec §11.3, §4.3.7 | Checkout Submission | TC-111, TC-140, TC-141, TC-142, TC-143, TC-144, TC-145, TC-146 | 8 | 2 | 1 | 5 |  | 0 | 0 | 0 | 0 | Covered | 0
FR-14 | Functional | Authentication | Users shall be able to attempt login with email and password | Spec §11.4, §4.4 | Login Form & Validation | TC-100, TC-101, TC-102, TC-103, TC-104, TC-106, TC-107, TC-108 | 8 |  | 3 | 3 | 2 | 0 | 0 | 0 | 0 | Covered | 0
FR-15 | Functional | Authentication | Social login link icons shall be displayed on the Login page | Spec §11.4, §4.4.3 | Social Login Display | TC-230 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | Covered | 0
FR-16 | Functional | Navigation | A persistent navigation bar shall be present on all pages | Spec §11.5, §3.1 | Persistent Navbar | TC-001, TC-002, TC-005, TC-008, TC-009, TC-245 | 6 | 2 |  |  | 4 | 0 | 0 | 0 | 0 | Covered | 0
FR-17 | Functional | Navigation | The active page shall be visually indicated in the navbar | Spec §11.5, §3.1 | Active Page Indicator | TC-003 | 1 |  |  | 1 |  | 0 | 0 | 0 | 0 | Covered | 0
FR-18 | Functional | Navigation | The logo shall link back to the homepage from all pages | Spec §11.5, §3.1 | Logo Home Link | TC-002, TC-004 | 2 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | Covered | 0
NFR-01 | Non-Functional | Usability | All forms shall display inline validation error messages | Spec §12.1 | Inline Error Messages | TC-070, TC-101, TC-111, TC-140, TC-143 | 5 | 2 | 2 | 1 |  | 0 | 0 | 0 | 0 | Covered | 0
NFR-02 | Non-Functional | Usability | The application shall be fully navigable without requiring login | Spec §12.1, §14.5 | Open Navigation (No Auth) | TC-001, TC-170, TC-206 | 3 | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | Covered | 0
NFR-03 | Non-Functional | Usability | Validation messages shall be displayed adjacent to the field that triggered them | Spec §12.1, §5.3 | Error-Field Adjacency | TC-143 | 1 |  |  | 1 |  | 0 | 0 | 0 | 0 | Covered | 0
NFR-04 | Non-Functional | Compatibility | The application is primarily designed for Google Chrome | Spec §12.2 | Chrome Compatibility | TC-180, TC-181, TC-240, TC-241 | 4 |  | 2 |  | 2 | 0 | 0 | 0 | 0 | Covered | 0
NFR-05 | Non-Functional | Compatibility | Basic functionality verified in Firefox and Safari | Spec §12.2 | Firefox + Safari Compatibility | TC-180, TC-181 | 2 |  | 2 |  |  | 0 | 0 | 0 | 0 | Covered | 0
NFR-06 | Non-Functional | Accessibility | Product images shall include descriptive alt text | Spec §12.3 | Image Alt Text | TC-210, TC-213, TC-215 | 3 |  |  | 2 | 1 | 0 | 0 | 0 | 0 | Covered | 0
NFR-07 | Non-Functional | Accessibility | Form inputs shall be associated with visible labels | Spec §12.3 | Form Label Association | TC-121, TC-122, TC-145, TC-211, TC-213, TC-214, TC-216 | 7 |  |  | 5 | 2 | 0 | 0 | 0 | 0 | Covered | 0
NFR-08 | Non-Functional | Accessibility | Error messages shall be programmatically associated with their fields | Spec §12.3 | Error-Field A11y Association | TC-212, TC-213, TC-217 | 3 |  |  | 2 | 1 | 0 | 0 | 0 | 0 | Covered | 0
TOTAL | [6 empty] | 161 | 33 | 41 | 53 | 34 | 0 | 0 | 0 | 0 | 26 of 26

## Test Case Master
TC ID | Module | Title | Priority | Type | Automation | Requirements | Defect Hint If Fails
TC-001 | Navigation | Verify all 5 pages load successfully via direct URL | P0 | Smoke | Smoke | FR-16 | Page-load failure / routing bug / broken build
TC-002 | Navigation | Verify navbar links navigate to correct pages | P0 | Functional | Smoke | FR-16, FR-18 | Routing / navbar link bug
TC-003 | Navigation | Verify navbar active-state highlight reflects current page | P2 | UI | Regression | FR-17 | CSS / active-state bug
TC-004 | Navigation | Verify logo from any page returns user to home | P2 | Functional | Regression | FR-18 | Logo link broken / wrong href
TC-005 | Navigation | Verify footer is present on all pages with correct copyright | P3 | UI | Regression | — | Footer template missing / wrong text
TC-006 | Navigation | Verify intentional broken /bout link is observable on Basket page | P3 | UI | Manual | Spec §17 (KI-1) | Documented intentional bug (KI-1) — verification only, NOT a real defect
TC-007 | Navigation | Verify navbar displays basket item count badge | P0 | Functional | Smoke | FR-05 | Basket counter not bound to state / live update broken
TC-008 | Navigation | Verify navbar basket count badge handles large numbers (10, 99, 100+) | P3 | Boundary | Manual | FR-05 | Layout regression — counter overflow / navbar wrapping
TC-009 | Navigation | Verify navbar position behaviour on long page scroll | P3 | UI | Manual | — | Sticky-header CSS regression / scroll behaviour bug
TC-010 | Home | Verify home page hero banner renders with correct title and tagline | P1 | UI | Regression | FR-03 | Hero asset missing / template content drift
TC-011 | Home | Verify Browse Sweets CTA navigates to /sweets | P2 | Functional | Regression | FR-03 | CTA link broken or wrong target URL
TC-012 | Home | Verify promotional banner displays 20% Off message | P3 | UI | Regression | — | Promo banner content drift / hidden by CSS
TC-013 | Home | Verify Most Popular section renders 4 featured products | P1 | UI | Regression | FR-03 | Featured-products data wrong / curated list mis-configured
TC-020 | Browse Sweets | Verify Browse Sweets page header renders correctly | P2 | UI | Regression | FR-01 | Static page text drift
TC-021 | Browse Sweets | Verify all 16 products render on /sweets (parameterised) | P0 | Functional | Regression | FR-01, FR-02 | Catalogue data mismatch with spec / image broken / layout regression
TC-022 | Browse Sweets | Verify product prices conform to documented price range | P2 | Boundary | Regression | FR-02 | Currency formatting bug / data drift
TC-023 | Browse Sweets | Verify product cards render in the documented spec order | P3 | UI | Regression | FR-01 | Catalogue order configuration drift
TC-024 | Browse Sweets | Verify long product descriptions wrap and render within card bounds | P3 | UI | Regression | FR-02 | CSS overflow / text-clipping bug on long descriptions
TC-025 | Browse Sweets | Verify product card layout consistency (all 16 cards same dimensions) | P3 | UI | Manual | FR-02 | CSS grid layout inconsistency / card-height misalignment
TC-026 | Browse Sweets | Verify broken-image behaviour for product cards | P3 | Negative | Manual | — | Missing image fallback / card collapses on broken image
TC-030 | Add to Basket | Verify Add to Basket from /sweets increments navbar count | P0 | Functional | Smoke | FR-04, FR-05 | Add-to-basket handler broken / counter not bound
TC-031 | Add to Basket | Verify Add to Basket from Home page Most Popular section | P0 | Functional | Smoke | FR-04, FR-05 | Add-to-basket from Home not wired / counter not updated
TC-032 | Add to Basket | Verify adding multiple different products updates count correctly | P0 | Functional | Regression | FR-05 | Counter aggregation bug / state mutation issue
TC-033 | Add to Basket | Verify adding same product multiple times increments quantity (not duplicate line) | P1 | Functional | Regression | FR-04 | Quantity merge bug — duplicate line items instead of qty++
TC-034 | Add to Basket | Verify Add to Basket persists across navigation | P0 | Persistence | Regression | FR-04, FR-05 | State persistence broken (in-memory only / wrong storage scope)
TC-035 | Add to Basket | Verify rapid double-click on Add to Basket adds expected number of items | P2 | Negative | Manual | FR-04 | Click debounce or double-handler bug
TC-036 | Add to Basket | Verify no network request is generated on Add to Basket | P2 | Security | Manual | — | Unintended network call / accidental telemetry
TC-037 | Add to Basket | Verify Add to Basket button remains active after each click | P2 | Functional | Regression | FR-04 | Button gets disabled / loses event handler
TC-038 | Add to Basket | Verify Add to Basket from Most Popular and Browse Sweets adds the SAME product to one line | P2 | Functional | Regression | FR-04 | Same-product-different-source treated as different items (duplicate-line bug)
TC-040 | Basket Page | Verify Basket page header renders correctly | P2 | UI | Regression | — | Static text drift on basket page
TC-041 | Basket Page | Verify empty basket state on /basket | P1 | Functional | Smoke | FR-09 | Empty-basket render bug / null-state crash
TC-042 | Basket Page | Verify basket page lists added items with quantities | P0 | Functional | Regression | FR-09 | Basket-state-to-UI render bug / wrong product binding
TC-043 | Basket Page | Verify subtotal on basket page equals sum of line subtotals | P0 | Functional | Regression | FR-09, FR-10 | Subtotal calculation bug / aggregation off
TC-044 | Basket Page | Verify basket line items maintain order across navigation and refresh | P3 | Persistence | Regression | FR-09 | Non-deterministic line ordering / state shuffles
TC-045 | Basket Page | Verify basket shows line-level subtotal for multi-quantity items | P2 | UI | Regression | FR-09 | Quantity / line-total display bug
TC-050 | Empty Basket | Verify Empty Basket clears all items and resets count to 0 | P1 | Functional | Regression | FR-06 | Empty Basket handler not wired / state not cleared
TC-051 | Empty Basket | Verify Empty Basket on already-empty basket has no negative effect | P3 | Negative | Manual | FR-06 | Null-state crash on empty-empty action
TC-060 | Delivery | Verify default delivery selection is Collect (FREE) | P1 | Functional | Regression | FR-07 | Default selection wrong / radio not pre-checked
TC-061 | Delivery | Verify selecting Standard Shipping adds £1.99 to order total | P0 | Functional | Smoke | FR-07, FR-10 | Delivery charge math wrong / total not updating
TC-062 | Delivery | Verify switching back to Collect removes the £1.99 charge | P1 | Functional | Regression | FR-07, FR-10 | Reverse-toggle bug — charge sticks after switch back
TC-063 | Delivery | Verify only one delivery option can be selected at a time (radio behaviour) | P2 | Functional | Regression | FR-07 | Radio group bug — both can be selected simultaneously
TC-064 | Delivery | Verify delivery option selection persists across navigation | P2 | Persistence | Manual | FR-07, Spec §5.1 | Delivery selection lost on navigation (state scope bug)
TC-070 | Promo Code | Verify invalid promo code triggers documented error message | P1 | Negative | Regression | FR-08 | Promo validation bug / wrong error message
TC-071 | Promo Code | Verify clicking Redeem with empty promo code field | P2 | Negative | Manual | FR-08 | Empty-input edge case crash / no validation
TC-072 | Promo Code | Verify whitespace-only promo code is treated as invalid | P3 | Negative | Manual | FR-08 | Trim() missing / whitespace accepted as valid
TC-073 | Promo Code | Verify promo code field is case-sensitivity behaviour | P3 | Negative | Manual | FR-08 | Case-sensitivity inconsistency
TC-074 | Promo Code | Verify long promo code string does not crash UI | P3 | Boundary | Manual | FR-08 | Long-input layout break / no max-length
TC-075 | Promo Code | Verify special characters in promo code field | P3 | Negative | Manual | FR-08 | Special-char handling / potential XSS hint
TC-076 | Promo Code | Verify valid promo code applies discount (TBD — code to be discovered) | P1 | Functional | Regression | FR-08 | Promo discount logic bug / wrong amount
TC-077 | Promo Code | Verify promo code can be applied with empty basket | P2 | Negative | Manual | FR-08 | Empty-basket + promo crash / negative total
TC-078 | Promo Code | Verify promo discount behaviour after Empty Basket | P3 | Persistence | Manual | FR-06, FR-08 | Promo state leak after Empty Basket / inconsistent behaviour
TC-079 | Promo Code | Verify promo + delivery interaction (discount applies to subtotal only or total?) | P2 | Functional | Manual | FR-08, FR-10, Spec §6.1 | Promo discount applied to delivery — diverges from Spec §6.1 formula
TC-080 | Calculation | Verify subtotal for single low-price item (£0.10) | P0 | Functional | Smoke | FR-09, FR-10 | Single-item subtotal calc bug
TC-081 | Calculation | Verify subtotal + Standard Shipping for two items | P0 | Functional | Regression | FR-09, FR-10 | Multi-item + delivery aggregation bug
TC-082 | Calculation | Verify quantity multiplication for same-product line | P0 | Functional | Regression | FR-09 | Quantity multiplication bug
TC-083 | Calculation | Verify single item with Standard Shipping | P0 | Functional | Regression | FR-09, FR-10 | Single item + delivery math bug
TC-084 | Calculation | Verify subtotal for full catalogue (one of each, 16 items) | P0 | Functional | Regression | FR-09 | Full-catalogue aggregation bug — most likely place for off-by-pence errors
TC-085 | Calculation | Verify total for full catalogue with Standard Shipping | P1 | Functional | Regression | FR-10 | Delivery additive bug at scale
TC-086 | Calculation | Verify rounding — Bubbly + Drumsticks must show £0.30 not £0.30000… | P0 | Boundary | Regression | FR-09 / Spec §6.3 | JS floating-point rounding bug (classic JS cart defect)
TC-087 | Calculation | Verify rounding — three-item combination producing fractional pence | P1 | Boundary | Regression | FR-09 / Spec §6.3 | JS floating-point rounding bug across more terms
TC-088 | Calculation | Verify empty basket subtotal is £0.00 | P2 | Functional | Regression | FR-09 / Spec §6.2 | Empty-basket subtotal bug — possibly NaN or undefined
TC-089 | Calculation | Verify behaviour: Standard Shipping selected on empty basket | P2 | Boundary | Manual | FR-10 / Spec §6.2 | Edge case: delivery applied without items (usability/calculation gap)
TC-090 | Calculation | Verify total updates dynamically as items are added on basket page | P1 | Functional | Manual | FR-10 | Stale-total bug — UI not re-rendered after state change
TC-091 | Calculation | Verify delivery toggle does not duplicate or lose items | P2 | Functional | Regression | FR-07, FR-09 | State-mutation-on-toggle bug — items lost or duplicated on radio change
TC-092 | Calculation | Verify high-quantity calculation (single product × 50) | P2 | Boundary | Manual | FR-09 | High-quantity overflow / display truncation
TC-093 | Calculation | Verify total formatting consistency (always 2 decimal places, GBP symbol) | P2 | UI | Regression | Spec §6.3 | Currency formatting inconsistency across totals
TC-094 | Calculation | Verify subtotal recomputes correctly after Empty Basket | P2 | Functional | Regression | FR-09 | Subtotal not recomputed after Empty Basket — stale value
TC-095 | Calculation | Verify decimal-rounding edge case: subtotal £1.99 with Standard delivery = £3.98 | P1 | Boundary | Regression | FR-09, FR-10, Spec §6.3 | JS floating-point rounding bug at delivery-charge addition
TC-096 | Calculation | Verify all 16 distinct items + Standard Shipping produces no float artefact | P1 | Boundary | Regression | FR-09, FR-10, Spec §6.3 | Worst-case JS floating-point bug — 16 items + delivery
TC-100 | Login | Verify Login page header renders correctly | P3 | UI | Regression | — | Static text drift on login page
TC-101 | Login | Verify Login form submission with both fields empty | P1 | Negative | Regression | FR-14 | Validation not wired / button submits empty form
TC-102 | Login | Verify Login form rejects malformed email addresses (parameterised) | P1 | Negative | Regression | FR-14, Spec §7.1 | Email regex too permissive — accepts malformed emails
TC-103 | Login | Verify Login form accepts well-formed email + non-empty password | P2 | Functional | Manual | FR-14 | Validation false-positive — rejects valid input
TC-104 | Login | Verify password field masks characters | P1 | Security | Regression | Spec §14.1 | Password not masked — security regression
TC-106 | Login | Verify Login form retains entered values after failed validation | P2 | UI | Manual | Spec §5.3 | Form-state-on-error bug — inputs cleared on validation fail
TC-107 | Login | Verify Login form does not auto-submit on Enter key in Email field | P2 | Functional | Manual | FR-14 | Enter-key bypasses validation / inconsistent form submit trigger
TC-108 | Login | Verify navbar does NOT change after login submit (no auth state UI) | P3 | Functional | Manual | Spec §9.4, Spec §17 (KI-4) | Auth state UI drift (KI-4 anchor)
TC-110 | Billing | Verify Billing form renders all 8 documented fields | P1 | UI | Regression | FR-11 | Form template missing fields / wrong labels
TC-111 | Billing | Verify Billing form — submit empty triggers all 7 required field errors | P0 | Negative | Regression | FR-11, FR-13, Spec §7.2 | Submit-empty validation gap / errors not shown simultaneously
TC-112 | Billing | Verify Billing — First Name validation (parameterised) | P1 | Negative | Regression | Spec §7.2 | First-name validation gap or wrong message
TC-113 | Billing | Verify Billing — Last Name validation | P1 | Negative | Regression | Spec §7.2 | Last-name validation gap or wrong message
TC-114 | Billing | Verify Billing — Email field validation (parameterised) | P1 | Negative | Regression | Spec §7.2 | Email validation regex bug
TC-115 | Billing | Verify Billing — Address Line 1 validation | P1 | Negative | Regression | Spec §7.2 | Address-line-1 validation gap
TC-116 | Billing | Verify Billing — Address Line 2 is optional | P2 | Functional | Regression | Spec §7.2 | Required-flag bug — Address 2 incorrectly required
TC-117 | Billing | Verify Billing — Country dropdown options and validation | P1 | Negative | Regression | Spec §4.3.5, §7.2 | Country dropdown options mis-configured
TC-118 | Billing | Verify Billing — City dropdown options and validation (KI-3) | P1 | Negative | Regression | Spec §4.3.5, §7.2, Spec §17 | City dropdown configuration drift (KI-3 anchor)
TC-119 | Billing | Verify Billing — ZIP / Postcode validation | P1 | Negative | Regression | Spec §7.2 | ZIP validation gap or wrong error
TC-120 | Billing | Verify Billing form retains values after failed validation | P2 | UI | Manual | Spec §5.3 | Form-state-on-error bug — values wiped on error
TC-121 | Billing | Verify Billing form Tab order is logical (top-to-bottom, left-to-right) | P2 | Accessibility | Manual | NFR-07 | Tab order broken — accessibility regression
TC-122 | Billing | Verify Billing form Tab continues into Payment form | P2 | Accessibility | Manual | NFR-07 | Focus trap inside billing form — keyboard users can't reach payment
TC-123 | Billing | Verify Billing email field rejects emails with leading/trailing whitespace | P2 | Negative | Manual | Spec §7.2 | Whitespace handling inconsistency in email field
TC-130 | Payment | Verify Payment form renders all 4 documented fields | P1 | UI | Regression | FR-12 | Payment template missing fields
TC-131 | Payment | Verify Payment — Name on Card validation | P1 | Negative | Regression | Spec §7.3 | Name-on-Card validation gap
TC-132 | Payment | Verify Payment — Card Number validation (parameterised) | P1 | Negative | Regression | Spec §7.3 | Card number Luhn / length validation gap (likely thin)
TC-133 | Payment | Verify Payment — Expiration Date validation | P1 | Negative | Regression | Spec §7.3 | Expiry past-date validation gap (likely thin)
TC-134 | Payment | Verify Payment — CVV validation (parameterised) | P1 | Boundary | Regression | Spec §7.3 | CVV length / format validation gap
TC-135 | Payment | Verify CVV field masks input (security) | P2 | Security | Manual | — | CVV not masked — minor security concern
TC-136 | Payment | Verify card number field accepts and properly handles paste with spaces | P2 | Functional | Manual | Spec §7.3 | Paste with spaces breaks card validation — usability gap
TC-137 | Payment | Verify autocomplete attribute behaviour on payment fields | P3 | Security | Manual | — | Wrong autocomplete tokens / card data persisted by browser
TC-138 | Payment | Verify card number field does not allow alphabetic characters | P2 | Negative | Regression | Spec §7.3 | Card number accepts non-numeric — validation gap
TC-140 | Checkout | Verify Continue to checkout triggers full validation across both forms | P0 | Negative | Regression | FR-13 | Validation orchestration bug — not all errors fire on submit
TC-141 | Checkout | Verify Continue to checkout with all valid data — observe behaviour | P1 | Functional | Regression | FR-13, Spec §17 | Happy-path crash / unexpected network call (KI-5 anchor)
TC-142 | Checkout | Verify Continue to checkout on empty basket | P2 | Negative | Manual | Spec §8.1 | Empty-basket checkout permitted (usability gap per Spec §8.1)
TC-143 | Checkout | Verify error messages are placed adjacent to their fields | P2 | UI | Regression | NFR-01, NFR-03 | Error-message placement bug — wrong field association
TC-144 | Checkout | Verify error message clears when user corrects the field | P2 | UI | Manual | Spec §7.5 | Stale-error bug — message persists after correction
TC-145 | Checkout | Verify focus lands on first errored field after failed submit | P2 | Accessibility | Manual | Spec §7.5, NFR-07 | No focus jump to first error — accessibility gap
TC-146 | Checkout | Verify URL stays on /basket after failed validation | P2 | Functional | Regression | FR-13 | Form submits to a different URL / page state lost
TC-150 | About | Verify About page promotional banner renders | P3 | UI | Regression | — | Promo banner missing on About page
TC-151 | About | Verify About page content renders | P3 | UI | Regression | — | About content drift
TC-161 | Persistence | Verify basket persistence across page refresh | P1 | Persistence | Manual | Spec §8.10 | Refresh wipes state — wrong storage mechanism (sessionStorage vs localStorage)
TC-162 | Persistence | Verify basket persistence across browser back/forward navigation | P1 | Persistence | Manual | Spec §8.9 | Back/forward state loss — browser-cache vs storage interaction bug
TC-163 | Persistence | Verify basket persistence across new browser tab (same URL) | P2 | Persistence | Manual | Spec §9.2 | Cross-tab state inconsistency (storage scope confirmation)
TC-164 | Persistence | Verify basket persistence across browser close/reopen | P2 | Persistence | Manual | Spec §9.2 | Browser-restart state loss (storage scope confirmation)
TC-165 | Persistence | Verify basket state can be inspected in DevTools Application panel | P3 | Persistence | Manual | Spec §15.3 | Storage key not discoverable / opaque structure (automation seeding blocker)
TC-166 | Persistence | Verify UI handles direct localStorage manipulation gracefully (KI test) | P3 | Security | Manual | Spec §14.4 | Crash on corrupt storage state (per Spec §14.4 — graceful degradation expected)
TC-167 | Persistence | Verify cross-tab basket sync — modify in one tab, observe in another | P2 | Persistence | Manual | Spec §9.2 | Cross-tab inconsistency / storage event listener missing
TC-168 | Persistence | Verify cross-tab race — empty in tab 1, observe in tab 2 | P3 | Persistence | Manual | Spec §9.2 | Stale state in second tab after Empty Basket
TC-169 | Persistence | Verify back button after Empty Basket does NOT restore basket | P3 | Persistence | Manual | Spec §8.9 | Browser cache restores empty basket — back/forward state bug
TC-170 | Negative Flows | Verify direct URL navigation to /basket with empty basket | P2 | Functional | Regression | Spec §8.8 | Direct-URL routing bug / empty-state render bug
TC-171 | Negative Flows | Verify behaviour on direct navigation to a non-existent URL | P3 | Negative | Manual | — | 404 / catch-all routing bug
TC-180 | Compatibility | Verify smoke suite passes on Firefox | P1 | Compatibility | Regression | NFR-04, NFR-05 | Browser-specific render or behaviour bug (Firefox)
TC-181 | Compatibility | Verify smoke suite passes on Safari | P1 | Compatibility | Manual | NFR-04, NFR-05 | Browser-specific render or behaviour bug (Safari)
TC-190 | Performance | Verify Home page initial load < 3 seconds on standard broadband | P1 | Performance | Manual | Spec §13.1 | Heavy initial payload / unoptimised assets
TC-191 | Performance | Verify navigation between pages < 1 second | P2 | Performance | Manual | Spec §13.1 | Slow internal navigation / route-handling cost
TC-192 | Performance | Verify Add to Basket response < 100ms | P2 | Performance | Manual | Spec §13.1 | Heavy client-side handler — perf bug on basket update
TC-193 | Performance | Verify Lighthouse Performance score on Home page | P2 | Performance | Manual | Spec §13.3 | Lighthouse score below threshold — multiple opportunities
TC-194 | Performance | Verify Lighthouse Performance score on /sweets page | P2 | Performance | Manual | Spec §13.3 | Lighthouse score below threshold — image-heavy /sweets page
TC-195 | Performance | Verify pages render under Slow 3G throttle | P3 | Performance | Manual | Spec §13.3 | Page broken under throttled network (timeout, asset drop)
TC-196 | Performance | Verify GIF banner asset size and loading approach | P3 | Performance | Manual | Spec §13.2 | Oversized GIF asset — opportunity, not defect
TC-197 | Performance | Verify /sweets product image loading does not block page interactivity | P2 | Performance | Manual | Spec §13.2 | Page blocks interactivity until images load — perf bug
TC-200 | Security | Verify XSS injection in text fields is treated as plain text (parameterised) | P1 | Security | Manual | Spec §14.3 | XSS vulnerability — major security defect
TC-201 | Security | Verify XSS injection on Login fields | P1 | Security | Manual | Spec §14.3 | XSS vulnerability on Login fields
TC-202 | Security | Verify zero network requests on Continue to checkout (no card data on the wire) | P0 | Security | Manual | Spec §14.2 | Card data on the wire — critical PCI concern
TC-203 | Security | Verify no card data is logged to browser console | P1 | Security | Manual | Spec §14.2 | Card data logged to console — PCI / data leak concern
TC-204 | Security | Verify HTTPS is used and no mixed content warnings | P2 | Security | Manual | Spec §14.6 | Mixed-content warning / non-HTTPS asset
TC-205 | Security | Verify no third-party tracking or analytics loaded | P3 | Security | Manual | Spec §16.1 | Unexpected 3rd-party tracking — privacy concern
TC-206 | Security | Verify direct URL access does not bypass any expected access control | P3 | Security | Manual | Spec §14.5 | Routing / access-control regression (per spec, all routes should be open)
TC-207 | Security | Verify card data is not stored in browser autofill memory after submission | P2 | Security | Manual | Spec §14.2 | Browser autofill stores card data — privacy concern
TC-208 | Security | Verify form action attribute does not leak to a real endpoint | P1 | Security | Manual | Spec §14.2 | Form action leaks to real endpoint — critical PCI concern
TC-210 | Accessibility | Verify all product images have descriptive alt text | P2 | Accessibility | Manual | NFR-06 | Missing alt text — accessibility regression
TC-211 | Accessibility | Verify all form inputs are associated with visible labels | P2 | Accessibility | Manual | NFR-07 | Missing label association — accessibility regression
TC-212 | Accessibility | Verify error messages are programmatically associated with their fields | P2 | Accessibility | Manual | NFR-08 | Missing aria-describedby / aria-invalid — screen-reader gap
TC-213 | Accessibility | Verify Lighthouse Accessibility audit on key pages | P2 | Accessibility | Manual | NFR-06, NFR-07, NFR-08 | Lighthouse a11y score low — multiple findings
TC-214 | Accessibility | Verify keyboard navigation through forms | P3 | Accessibility | Manual | NFR-07 | Tab order broken / keyboard trap
TC-215 | Accessibility | Verify color contrast on primary text and error messages | P3 | Accessibility | Manual | NFR-06 | Color contrast below WCAG AA — accessibility defect
TC-216 | Accessibility | Verify focus indicator is visible on all interactive elements | P3 | Accessibility | Manual | NFR-07 | Missing focus indicators — keyboard users can't track focus
TC-217 | Accessibility | Verify basket count change is announceable to screen readers | P3 | Accessibility | Manual | FR-05, NFR-08 | No aria-live on counter — screen-reader users miss state changes
TC-220 | DevTools | Verify no critical JS errors on initial load of any page | P1 | Functional | Manual | Spec §15.3 | Pre-existing console errors (some intentional per Spec §17)
TC-221 | DevTools | Verify Network tab shows expected static asset loads only | P3 | Security | Manual | — | Unexpected 3rd-party network calls
TC-222 | DevTools | Verify Sources tab exposes basket logic and price calculation functions | P3 | Functional | Manual | Spec §15.4 | Source-tab inspection (no defect surface — discovery only)
TC-223 | DevTools | Verify Application Storage panel shows basket key after items added | P3 | Persistence | Manual | Spec §15.3 | Storage key not visible / not parseable
TC-230 | Known Issues | Verify KI register matches Spec §17 — full pass | P3 | Functional | Manual | Spec §17 | Documented intentional issues (KI-1..7) — these are NOT defects; verify they remain stable
TC-240 | Cross-cutting | Verify behaviour at 200% browser zoom | P3 | UI | Manual | NFR-04 | Layout breaks at high zoom — accessibility regression
TC-241 | Cross-cutting | Verify behaviour at narrow viewport (1024px wide) | P3 | UI | Manual | NFR-04 | Layout breaks at narrow viewport — responsive design gap
TC-242 | Cross-cutting | Verify text selection and copy behaviour on page content | P3 | UI | Manual | — | user-select: none disables text copy — usability regression
TC-243 | Cross-cutting | Verify URL behaviour on hash change and query string | P3 | Negative | Manual | — | Routing crashes on query-string or hash — fragile router
TC-244 | Cross-cutting | Verify behaviour in incognito / private browsing mode | P3 | Persistence | Manual | Spec §9.2 | Storage-restricted environment crashes app
TC-245 | Cross-cutting | Verify favicon loads on all pages | P3 | UI | Manual | — | Missing favicon — branding / polish gap

## RTM (Reverse)
TC ID | Title | Priority | Module | Requirement(s) Covered | Trace Status
TC-001 | Verify all 5 pages load successfully via direct URL | P0 | Navigation | FR-16, NFR-02 | Traced
TC-002 | Verify navbar links navigate to correct pages | P0 | Navigation | FR-16, FR-18 | Traced
TC-003 | Verify navbar active-state highlight reflects current page | P2 | Navigation | FR-17 | Traced
TC-004 | Verify logo from any page returns user to home | P2 | Navigation | FR-18 | Traced
TC-005 | Verify footer is present on all pages with correct copyright | P3 | Navigation | FR-16 | Traced
TC-006 | Verify intentional broken /bout link is observable on Basket page | P3 | Navigation | — | Orphan (review)
TC-007 | Verify navbar displays basket item count badge | P0 | Navigation | FR-05 | Traced
TC-008 | Verify navbar basket count badge handles large numbers (10, 99, 100+) | P3 | Navigation | FR-05, FR-16 | Traced
TC-009 | Verify navbar position behaviour on long page scroll | P3 | Navigation | FR-16 | Traced
TC-010 | Verify home page hero banner renders with correct title and tagline | P1 | Home | FR-03 | Traced
TC-011 | Verify Browse Sweets CTA navigates to /sweets | P2 | Home | FR-03 | Traced
TC-012 | Verify promotional banner displays 20% Off message | P3 | Home | FR-03 | Traced
TC-013 | Verify Most Popular section renders 4 featured products | P1 | Home | FR-03 | Traced
TC-020 | Verify Browse Sweets page header renders correctly | P2 | Browse Sweets | FR-01 | Traced
TC-021 | Verify all 16 products render on /sweets (parameterised) | P0 | Browse Sweets | FR-01, FR-02 | Traced
TC-022 | Verify product prices conform to documented price range | P2 | Browse Sweets | FR-01, FR-02 | Traced
TC-023 | Verify product cards render in the documented spec order | P3 | Browse Sweets | FR-01 | Traced
TC-024 | Verify long product descriptions wrap and render within card bounds | P3 | Browse Sweets | FR-01, FR-02 | Traced
TC-025 | Verify product card layout consistency (all 16 cards same dimensions) | P3 | Browse Sweets | FR-01, FR-02 | Traced
TC-026 | Verify broken-image behaviour for product cards | P3 | Browse Sweets | FR-01, FR-02 | Traced
TC-030 | Verify Add to Basket from /sweets increments navbar count | P0 | Add to Basket | FR-04, FR-05 | Traced
TC-031 | Verify Add to Basket from Home page Most Popular section | P0 | Add to Basket | FR-04, FR-05 | Traced
TC-032 | Verify adding multiple different products updates count correctly | P0 | Add to Basket | FR-05 | Traced
TC-033 | Verify adding same product multiple times increments quantity (not duplicate line) | P1 | Add to Basket | FR-04 | Traced
TC-034 | Verify Add to Basket persists across navigation | P0 | Add to Basket | FR-04, FR-05 | Traced
TC-035 | Verify rapid double-click on Add to Basket adds expected number of items | P2 | Add to Basket | FR-04 | Traced
TC-036 | Verify no network request is generated on Add to Basket | P2 | Add to Basket | FR-04 | Traced
TC-037 | Verify Add to Basket button remains active after each click | P2 | Add to Basket | FR-04 | Traced
TC-038 | Verify Add to Basket from Most Popular and Browse Sweets adds the SAME product to one line | P2 | Add to Basket | FR-04 | Traced
TC-040 | Verify Basket page header renders correctly | P2 | Basket Page | — | Orphan (review)
TC-041 | Verify empty basket state on /basket | P1 | Basket Page | FR-09 | Traced
TC-042 | Verify basket page lists added items with quantities | P0 | Basket Page | FR-09 | Traced
TC-043 | Verify subtotal on basket page equals sum of line subtotals | P0 | Basket Page | FR-09, FR-10 | Traced
TC-044 | Verify basket line items maintain order across navigation and refresh | P3 | Basket Page | FR-09 | Traced
TC-045 | Verify basket shows line-level subtotal for multi-quantity items | P2 | Basket Page | FR-09 | Traced
TC-050 | Verify Empty Basket clears all items and resets count to 0 | P1 | Empty Basket | FR-05, FR-06 | Traced
TC-051 | Verify Empty Basket on already-empty basket has no negative effect | P3 | Empty Basket | FR-06 | Traced
TC-060 | Verify default delivery selection is Collect (FREE) | P1 | Delivery | FR-07 | Traced
TC-061 | Verify selecting Standard Shipping adds £1.99 to order total | P0 | Delivery | FR-07, FR-10 | Traced
TC-062 | Verify switching back to Collect removes the £1.99 charge | P1 | Delivery | FR-07, FR-10 | Traced
TC-063 | Verify only one delivery option can be selected at a time (radio behaviour) | P2 | Delivery | FR-07 | Traced
TC-064 | Verify delivery option selection persists across navigation | P2 | Delivery | FR-07 | Traced
TC-070 | Verify invalid promo code triggers documented error message | P1 | Promo Code | FR-08, NFR-01 | Traced
TC-071 | Verify clicking Redeem with empty promo code field | P2 | Promo Code | FR-08 | Traced
TC-072 | Verify whitespace-only promo code is treated as invalid | P3 | Promo Code | FR-08 | Traced
TC-073 | Verify promo code field is case-sensitivity behaviour | P3 | Promo Code | FR-08 | Traced
TC-074 | Verify long promo code string does not crash UI | P3 | Promo Code | FR-08 | Traced
TC-075 | Verify special characters in promo code field | P3 | Promo Code | FR-08 | Traced
TC-076 | Verify valid promo code applies discount (TBD — code to be discovered) | P1 | Promo Code | FR-08 | Traced
TC-077 | Verify promo code can be applied with empty basket | P2 | Promo Code | FR-08 | Traced
TC-078 | Verify promo discount behaviour after Empty Basket | P3 | Promo Code | FR-06, FR-08 | Traced
TC-079 | Verify promo + delivery interaction (discount applies to subtotal only or total?) | P2 | Promo Code | FR-08, FR-10 | Traced
TC-080 | Verify subtotal for single low-price item (£0.10) | P0 | Calculation | FR-09, FR-10 | Traced
TC-081 | Verify subtotal + Standard Shipping for two items | P0 | Calculation | FR-09, FR-10 | Traced
TC-082 | Verify quantity multiplication for same-product line | P0 | Calculation | FR-09 | Traced
TC-083 | Verify single item with Standard Shipping | P0 | Calculation | FR-09, FR-10 | Traced
TC-084 | Verify subtotal for full catalogue (one of each, 16 items) | P0 | Calculation | FR-09 | Traced
TC-085 | Verify total for full catalogue with Standard Shipping | P1 | Calculation | FR-10 | Traced
TC-086 | Verify rounding — Bubbly + Drumsticks must show £0.30 not £0.30000… | P0 | Calculation | FR-09 | Traced
TC-087 | Verify rounding — three-item combination producing fractional pence | P1 | Calculation | FR-09 | Traced
TC-088 | Verify empty basket subtotal is £0.00 | P2 | Calculation | FR-09 | Traced
TC-089 | Verify behaviour: Standard Shipping selected on empty basket | P2 | Calculation | FR-10 | Traced
TC-090 | Verify total updates dynamically as items are added on basket page | P1 | Calculation | FR-10 | Traced
TC-091 | Verify delivery toggle does not duplicate or lose items | P2 | Calculation | FR-07, FR-09 | Traced
TC-092 | Verify high-quantity calculation (single product × 50) | P2 | Calculation | FR-09 | Traced
TC-093 | Verify total formatting consistency (always 2 decimal places, GBP symbol) | P2 | Calculation | FR-09 | Traced
TC-094 | Verify subtotal recomputes correctly after Empty Basket | P2 | Calculation | FR-06, FR-09 | Traced
TC-095 | Verify decimal-rounding edge case: subtotal £1.99 with Standard delivery = £3.98 | P1 | Calculation | FR-09, FR-10 | Traced
TC-096 | Verify all 16 distinct items + Standard Shipping produces no float artefact | P1 | Calculation | FR-09, FR-10 | Traced
TC-100 | Verify Login page header renders correctly | P3 | Login | FR-14 | Traced
TC-101 | Verify Login form submission with both fields empty | P1 | Login | FR-14, NFR-01 | Traced
TC-102 | Verify Login form rejects malformed email addresses (parameterised) | P1 | Login | FR-14 | Traced
TC-103 | Verify Login form accepts well-formed email + non-empty password | P2 | Login | FR-14 | Traced
TC-104 | Verify password field masks characters | P1 | Login | FR-14 | Traced
TC-106 | Verify Login form retains entered values after failed validation | P2 | Login | FR-14 | Traced
TC-107 | Verify Login form does not auto-submit on Enter key in Email field | P2 | Login | FR-14 | Traced
TC-108 | Verify navbar does NOT change after login submit (no auth state UI) | P3 | Login | FR-14 | Traced
TC-110 | Verify Billing form renders all 8 documented fields | P1 | Billing | FR-11 | Traced
TC-111 | Verify Billing form — submit empty triggers all 7 required field errors | P0 | Billing | FR-11, FR-13, NFR-01 | Traced
TC-112 | Verify Billing — First Name validation (parameterised) | P1 | Billing | FR-11 | Traced
TC-113 | Verify Billing — Last Name validation | P1 | Billing | FR-11 | Traced
TC-114 | Verify Billing — Email field validation (parameterised) | P1 | Billing | FR-11 | Traced
TC-115 | Verify Billing — Address Line 1 validation | P1 | Billing | FR-11 | Traced
TC-116 | Verify Billing — Address Line 2 is optional | P2 | Billing | FR-11 | Traced
TC-117 | Verify Billing — Country dropdown options and validation | P1 | Billing | FR-11 | Traced
TC-118 | Verify Billing — City dropdown options and validation (KI-3) | P1 | Billing | FR-11 | Traced
TC-119 | Verify Billing — ZIP / Postcode validation | P1 | Billing | FR-11 | Traced
TC-120 | Verify Billing form retains values after failed validation | P2 | Billing | FR-11 | Traced
TC-121 | Verify Billing form Tab order is logical (top-to-bottom, left-to-right) | P2 | Billing | FR-11, NFR-07 | Traced
TC-122 | Verify Billing form Tab continues into Payment form | P2 | Billing | FR-11, NFR-07 | Traced
TC-123 | Verify Billing email field rejects emails with leading/trailing whitespace | P2 | Billing | FR-11 | Traced
TC-130 | Verify Payment form renders all 4 documented fields | P1 | Payment | FR-12 | Traced
TC-131 | Verify Payment — Name on Card validation | P1 | Payment | FR-12 | Traced
TC-132 | Verify Payment — Card Number validation (parameterised) | P1 | Payment | FR-12 | Traced
TC-133 | Verify Payment — Expiration Date validation | P1 | Payment | FR-12 | Traced
TC-134 | Verify Payment — CVV validation (parameterised) | P1 | Payment | FR-12 | Traced
TC-135 | Verify CVV field masks input (security) | P2 | Payment | FR-12 | Traced
TC-136 | Verify card number field accepts and properly handles paste with spaces | P2 | Payment | FR-12 | Traced
TC-137 | Verify autocomplete attribute behaviour on payment fields | P3 | Payment | FR-12 | Traced
TC-138 | Verify card number field does not allow alphabetic characters | P2 | Payment | FR-12 | Traced
TC-140 | Verify Continue to checkout triggers full validation across both forms | P0 | Checkout | FR-13, NFR-01 | Traced
TC-141 | Verify Continue to checkout with all valid data — observe behaviour | P1 | Checkout | FR-13 | Traced
TC-142 | Verify Continue to checkout on empty basket | P2 | Checkout | FR-13 | Traced
TC-143 | Verify error messages are placed adjacent to their fields | P2 | Checkout | FR-13, NFR-01, NFR-03 | Traced
TC-144 | Verify error message clears when user corrects the field | P2 | Checkout | FR-13 | Traced
TC-145 | Verify focus lands on first errored field after failed submit | P2 | Checkout | FR-13, NFR-07 | Traced
TC-146 | Verify URL stays on /basket after failed validation | P2 | Checkout | FR-13 | Traced
TC-150 | Verify About page promotional banner renders | P3 | About | — | Orphan (review)
TC-151 | Verify About page content renders | P3 | About | — | Orphan (review)
TC-161 | Verify basket persistence across page refresh | P1 | Persistence | — | Orphan (review)
TC-162 | Verify basket persistence across browser back/forward navigation | P1 | Persistence | — | Orphan (review)
TC-163 | Verify basket persistence across new browser tab (same URL) | P2 | Persistence | — | Orphan (review)
TC-164 | Verify basket persistence across browser close/reopen | P2 | Persistence | — | Orphan (review)
TC-165 | Verify basket state can be inspected in DevTools Application panel | P3 | Persistence | — | Orphan (review)
TC-166 | Verify UI handles direct localStorage manipulation gracefully (KI test) | P3 | Persistence | — | Orphan (review)
TC-167 | Verify cross-tab basket sync — modify in one tab, observe in another | P2 | Persistence | — | Orphan (review)
TC-168 | Verify cross-tab race — empty in tab 1, observe in tab 2 | P3 | Persistence | — | Orphan (review)
TC-169 | Verify back button after Empty Basket does NOT restore basket | P3 | Persistence | FR-06 | Traced
TC-170 | Verify direct URL navigation to /basket with empty basket | P2 | Negative Flows | NFR-02 | Traced
TC-171 | Verify behaviour on direct navigation to a non-existent URL | P3 | Negative Flows | — | Orphan (review)
TC-180 | Verify smoke suite passes on Firefox | P1 | Compatibility | NFR-04, NFR-05 | Traced
TC-181 | Verify smoke suite passes on Safari | P1 | Compatibility | NFR-04, NFR-05 | Traced
TC-190 | Verify Home page initial load < 3 seconds on standard broadband | P1 | Performance | — | Orphan (review)
TC-191 | Verify navigation between pages < 1 second | P2 | Performance | — | Orphan (review)
TC-192 | Verify Add to Basket response < 100ms | P2 | Performance | — | Orphan (review)
TC-193 | Verify Lighthouse Performance score on Home page | P2 | Performance | — | Orphan (review)
TC-194 | Verify Lighthouse Performance score on /sweets page | P2 | Performance | — | Orphan (review)
TC-195 | Verify pages render under Slow 3G throttle | P3 | Performance | — | Orphan (review)
TC-196 | Verify GIF banner asset size and loading approach | P3 | Performance | — | Orphan (review)
TC-197 | Verify /sweets product image loading does not block page interactivity | P2 | Performance | — | Orphan (review)
TC-200 | Verify XSS injection in text fields is treated as plain text (parameterised) | P1 | Security | — | Orphan (review)
TC-201 | Verify XSS injection on Login fields | P1 | Security | — | Orphan (review)
TC-202 | Verify zero network requests on Continue to checkout (no card data on the wire) | P0 | Security | — | Orphan (review)
TC-203 | Verify no card data is logged to browser console | P1 | Security | — | Orphan (review)
TC-204 | Verify HTTPS is used and no mixed content warnings | P2 | Security | — | Orphan (review)
TC-205 | Verify no third-party tracking or analytics loaded | P3 | Security | — | Orphan (review)
TC-206 | Verify direct URL access does not bypass any expected access control | P3 | Security | NFR-02 | Traced
TC-207 | Verify card data is not stored in browser autofill memory after submission | P2 | Security | — | Orphan (review)
TC-208 | Verify form action attribute does not leak to a real endpoint | P1 | Security | — | Orphan (review)
TC-210 | Verify all product images have descriptive alt text | P2 | Accessibility | NFR-06 | Traced
TC-211 | Verify all form inputs are associated with visible labels | P2 | Accessibility | NFR-07 | Traced
TC-212 | Verify error messages are programmatically associated with their fields | P2 | Accessibility | NFR-08 | Traced
TC-213 | Verify Lighthouse Accessibility audit on key pages | P2 | Accessibility | NFR-06, NFR-07, NFR-08 | Traced
TC-214 | Verify keyboard navigation through forms | P3 | Accessibility | NFR-07 | Traced
TC-215 | Verify color contrast on primary text and error messages | P3 | Accessibility | NFR-06 | Traced
TC-216 | Verify focus indicator is visible on all interactive elements | P3 | Accessibility | NFR-07 | Traced
TC-217 | Verify basket count change is announceable to screen readers | P3 | Accessibility | FR-05, NFR-08 | Traced
TC-220 | Verify no critical JS errors on initial load of any page | P1 | DevTools | — | Orphan (review)
TC-221 | Verify Network tab shows expected static asset loads only | P3 | DevTools | — | Orphan (review)
TC-222 | Verify Sources tab exposes basket logic and price calculation functions | P3 | DevTools | — | Orphan (review)
TC-223 | Verify Application Storage panel shows basket key after items added | P3 | DevTools | — | Orphan (review)
TC-230 | Verify KI register matches Spec §17 — full pass | P3 | Known Issues | FR-15 | Traced
TC-240 | Verify behaviour at 200% browser zoom | P3 | Cross-cutting | NFR-04 | Traced
TC-241 | Verify behaviour at narrow viewport (1024px wide) | P3 | Cross-cutting | NFR-04 | Traced
TC-242 | Verify text selection and copy behaviour on page content | P3 | Cross-cutting | — | Orphan (review)
TC-243 | Verify URL behaviour on hash change and query string | P3 | Cross-cutting | — | Orphan (review)
TC-244 | Verify behaviour in incognito / private browsing mode | P3 | Cross-cutting | — | Orphan (review)
TC-245 | Verify favicon loads on all pages | P3 | Cross-cutting | FR-16 | Traced

## Execution Log
TC ID | Title | Priority | Module | Automation | Status | Executed By | Execution Date | Defect ID | Notes
TC-001 | Verify all 5 pages load successfully via direct URL | P0 | Navigation | Smoke | Not Run
TC-002 | Verify navbar links navigate to correct pages | P0 | Navigation | Smoke | Not Run
TC-003 | Verify navbar active-state highlight reflects current page | P2 | Navigation | Regression | Not Run
TC-004 | Verify logo from any page returns user to home | P2 | Navigation | Regression | Not Run
TC-005 | Verify footer is present on all pages with correct copyright | P3 | Navigation | Regression | Not Run
TC-006 | Verify intentional broken /bout link is observable on Basket page | P3 | Navigation | Manual | Not Run
TC-007 | Verify navbar displays basket item count badge | P0 | Navigation | Smoke | Not Run
TC-008 | Verify navbar basket count badge handles large numbers (10, 99, 100+) | P3 | Navigation | Manual | Not Run
TC-009 | Verify navbar position behaviour on long page scroll | P3 | Navigation | Manual | Not Run
TC-010 | Verify home page hero banner renders with correct title and tagline | P1 | Home | Regression | Not Run
TC-011 | Verify Browse Sweets CTA navigates to /sweets | P2 | Home | Regression | Not Run
TC-012 | Verify promotional banner displays 20% Off message | P3 | Home | Regression | Not Run
TC-013 | Verify Most Popular section renders 4 featured products | P1 | Home | Regression | Not Run
TC-020 | Verify Browse Sweets page header renders correctly | P2 | Browse Sweets | Regression | Not Run
TC-021 | Verify all 16 products render on /sweets (parameterised) | P0 | Browse Sweets | Regression | Not Run
TC-022 | Verify product prices conform to documented price range | P2 | Browse Sweets | Regression | Not Run
TC-023 | Verify product cards render in the documented spec order | P3 | Browse Sweets | Regression | Not Run
TC-024 | Verify long product descriptions wrap and render within card bounds | P3 | Browse Sweets | Regression | Not Run
TC-025 | Verify product card layout consistency (all 16 cards same dimensions) | P3 | Browse Sweets | Manual | Not Run
TC-026 | Verify broken-image behaviour for product cards | P3 | Browse Sweets | Manual | Not Run
TC-030 | Verify Add to Basket from /sweets increments navbar count | P0 | Add to Basket | Smoke | Not Run
TC-031 | Verify Add to Basket from Home page Most Popular section | P0 | Add to Basket | Smoke | Not Run
TC-032 | Verify adding multiple different products updates count correctly | P0 | Add to Basket | Regression | Not Run
TC-033 | Verify adding same product multiple times increments quantity (not duplicate line) | P1 | Add to Basket | Regression | Not Run
TC-034 | Verify Add to Basket persists across navigation | P0 | Add to Basket | Regression | Not Run
TC-035 | Verify rapid double-click on Add to Basket adds expected number of items | P2 | Add to Basket | Manual | Not Run
TC-036 | Verify no network request is generated on Add to Basket | P2 | Add to Basket | Manual | Not Run
TC-037 | Verify Add to Basket button remains active after each click | P2 | Add to Basket | Regression | Not Run
TC-038 | Verify Add to Basket from Most Popular and Browse Sweets adds the SAME product to one line | P2 | Add to Basket | Regression | Not Run
TC-040 | Verify Basket page header renders correctly | P2 | Basket Page | Regression | Not Run
TC-041 | Verify empty basket state on /basket | P1 | Basket Page | Smoke | Not Run
TC-042 | Verify basket page lists added items with quantities | P0 | Basket Page | Regression | Not Run
TC-043 | Verify subtotal on basket page equals sum of line subtotals | P0 | Basket Page | Regression | Not Run
TC-044 | Verify basket line items maintain order across navigation and refresh | P3 | Basket Page | Regression | Not Run
TC-045 | Verify basket shows line-level subtotal for multi-quantity items | P2 | Basket Page | Regression | Not Run
TC-050 | Verify Empty Basket clears all items and resets count to 0 | P1 | Empty Basket | Regression | Not Run
TC-051 | Verify Empty Basket on already-empty basket has no negative effect | P3 | Empty Basket | Manual | Not Run
TC-060 | Verify default delivery selection is Collect (FREE) | P1 | Delivery | Regression | Not Run
TC-061 | Verify selecting Standard Shipping adds £1.99 to order total | P0 | Delivery | Smoke | Not Run
TC-062 | Verify switching back to Collect removes the £1.99 charge | P1 | Delivery | Regression | Not Run
TC-063 | Verify only one delivery option can be selected at a time (radio behaviour) | P2 | Delivery | Regression | Not Run
TC-064 | Verify delivery option selection persists across navigation | P2 | Delivery | Manual | Not Run
TC-070 | Verify invalid promo code triggers documented error message | P1 | Promo Code | Regression | Not Run
TC-071 | Verify clicking Redeem with empty promo code field | P2 | Promo Code | Manual | Not Run
TC-072 | Verify whitespace-only promo code is treated as invalid | P3 | Promo Code | Manual | Not Run
TC-073 | Verify promo code field is case-sensitivity behaviour | P3 | Promo Code | Manual | Not Run
TC-074 | Verify long promo code string does not crash UI | P3 | Promo Code | Manual | Not Run
TC-075 | Verify special characters in promo code field | P3 | Promo Code | Manual | Not Run
TC-076 | Verify valid promo code applies discount (TBD — code to be discovered) | P1 | Promo Code | Regression | Not Run
TC-077 | Verify promo code can be applied with empty basket | P2 | Promo Code | Manual | Not Run
TC-078 | Verify promo discount behaviour after Empty Basket | P3 | Promo Code | Manual | Not Run
TC-079 | Verify promo + delivery interaction (discount applies to subtotal only or total?) | P2 | Promo Code | Manual | Not Run
TC-080 | Verify subtotal for single low-price item (£0.10) | P0 | Calculation | Smoke | Not Run
TC-081 | Verify subtotal + Standard Shipping for two items | P0 | Calculation | Regression | Not Run
TC-082 | Verify quantity multiplication for same-product line | P0 | Calculation | Regression | Not Run
TC-083 | Verify single item with Standard Shipping | P0 | Calculation | Regression | Not Run
TC-084 | Verify subtotal for full catalogue (one of each, 16 items) | P0 | Calculation | Regression | Not Run
TC-085 | Verify total for full catalogue with Standard Shipping | P1 | Calculation | Regression | Not Run
TC-086 | Verify rounding — Bubbly + Drumsticks must show £0.30 not £0.30000… | P0 | Calculation | Regression | Not Run
TC-087 | Verify rounding — three-item combination producing fractional pence | P1 | Calculation | Regression | Not Run
TC-088 | Verify empty basket subtotal is £0.00 | P2 | Calculation | Regression | Not Run
TC-089 | Verify behaviour: Standard Shipping selected on empty basket | P2 | Calculation | Manual | Not Run
TC-090 | Verify total updates dynamically as items are added on basket page | P1 | Calculation | Manual | Not Run
TC-091 | Verify delivery toggle does not duplicate or lose items | P2 | Calculation | Regression | Not Run
TC-092 | Verify high-quantity calculation (single product × 50) | P2 | Calculation | Manual | Not Run
TC-093 | Verify total formatting consistency (always 2 decimal places, GBP symbol) | P2 | Calculation | Regression | Not Run
TC-094 | Verify subtotal recomputes correctly after Empty Basket | P2 | Calculation | Regression | Not Run
TC-095 | Verify decimal-rounding edge case: subtotal £1.99 with Standard delivery = £3.98 | P1 | Calculation | Regression | Not Run
TC-096 | Verify all 16 distinct items + Standard Shipping produces no float artefact | P1 | Calculation | Regression | Not Run
TC-100 | Verify Login page header renders correctly | P3 | Login | Regression | Not Run
TC-101 | Verify Login form submission with both fields empty | P1 | Login | Regression | Not Run
TC-102 | Verify Login form rejects malformed email addresses (parameterised) | P1 | Login | Regression | Not Run
TC-103 | Verify Login form accepts well-formed email + non-empty password | P2 | Login | Manual | Not Run
TC-104 | Verify password field masks characters | P1 | Login | Regression | Not Run
TC-106 | Verify Login form retains entered values after failed validation | P2 | Login | Manual | Not Run
TC-107 | Verify Login form does not auto-submit on Enter key in Email field | P2 | Login | Manual | Not Run
TC-108 | Verify navbar does NOT change after login submit (no auth state UI) | P3 | Login | Manual | Not Run
TC-110 | Verify Billing form renders all 8 documented fields | P1 | Billing | Regression | Not Run
TC-111 | Verify Billing form — submit empty triggers all 7 required field errors | P0 | Billing | Regression | Not Run
TC-112 | Verify Billing — First Name validation (parameterised) | P1 | Billing | Regression | Not Run
TC-113 | Verify Billing — Last Name validation | P1 | Billing | Regression | Not Run
TC-114 | Verify Billing — Email field validation (parameterised) | P1 | Billing | Regression | Not Run
TC-115 | Verify Billing — Address Line 1 validation | P1 | Billing | Regression | Not Run
TC-116 | Verify Billing — Address Line 2 is optional | P2 | Billing | Regression | Not Run
TC-117 | Verify Billing — Country dropdown options and validation | P1 | Billing | Regression | Not Run
TC-118 | Verify Billing — City dropdown options and validation (KI-3) | P1 | Billing | Regression | Not Run
TC-119 | Verify Billing — ZIP / Postcode validation | P1 | Billing | Regression | Not Run
TC-120 | Verify Billing form retains values after failed validation | P2 | Billing | Manual | Not Run
TC-121 | Verify Billing form Tab order is logical (top-to-bottom, left-to-right) | P2 | Billing | Manual | Not Run
TC-122 | Verify Billing form Tab continues into Payment form | P2 | Billing | Manual | Not Run
TC-123 | Verify Billing email field rejects emails with leading/trailing whitespace | P2 | Billing | Manual | Not Run
TC-130 | Verify Payment form renders all 4 documented fields | P1 | Payment | Regression | Not Run
TC-131 | Verify Payment — Name on Card validation | P1 | Payment | Regression | Not Run
TC-132 | Verify Payment — Card Number validation (parameterised) | P1 | Payment | Regression | Not Run
TC-133 | Verify Payment — Expiration Date validation | P1 | Payment | Regression | Not Run
TC-134 | Verify Payment — CVV validation (parameterised) | P1 | Payment | Regression | Not Run
TC-135 | Verify CVV field masks input (security) | P2 | Payment | Manual | Not Run
TC-136 | Verify card number field accepts and properly handles paste with spaces | P2 | Payment | Manual | Not Run
TC-137 | Verify autocomplete attribute behaviour on payment fields | P3 | Payment | Manual | Not Run
TC-138 | Verify card number field does not allow alphabetic characters | P2 | Payment | Regression | Not Run
TC-140 | Verify Continue to checkout triggers full validation across both forms | P0 | Checkout | Regression | Not Run
TC-141 | Verify Continue to checkout with all valid data — observe behaviour | P1 | Checkout | Regression | Not Run
TC-142 | Verify Continue to checkout on empty basket | P2 | Checkout | Manual | Not Run
TC-143 | Verify error messages are placed adjacent to their fields | P2 | Checkout | Regression | Not Run
TC-144 | Verify error message clears when user corrects the field | P2 | Checkout | Manual | Not Run
TC-145 | Verify focus lands on first errored field after failed submit | P2 | Checkout | Manual | Not Run
TC-146 | Verify URL stays on /basket after failed validation | P2 | Checkout | Regression | Not Run
TC-150 | Verify About page promotional banner renders | P3 | About | Regression | Not Run
TC-151 | Verify About page content renders | P3 | About | Regression | Not Run
TC-161 | Verify basket persistence across page refresh | P1 | Persistence | Manual | Not Run
TC-162 | Verify basket persistence across browser back/forward navigation | P1 | Persistence | Manual | Not Run
TC-163 | Verify basket persistence across new browser tab (same URL) | P2 | Persistence | Manual | Not Run
TC-164 | Verify basket persistence across browser close/reopen | P2 | Persistence | Manual | Not Run
TC-165 | Verify basket state can be inspected in DevTools Application panel | P3 | Persistence | Manual | Not Run
TC-166 | Verify UI handles direct localStorage manipulation gracefully (KI test) | P3 | Persistence | Manual | Not Run
TC-167 | Verify cross-tab basket sync — modify in one tab, observe in another | P2 | Persistence | Manual | Not Run
TC-168 | Verify cross-tab race — empty in tab 1, observe in tab 2 | P3 | Persistence | Manual | Not Run
TC-169 | Verify back button after Empty Basket does NOT restore basket | P3 | Persistence | Manual | Not Run
TC-170 | Verify direct URL navigation to /basket with empty basket | P2 | Negative Flows | Regression | Not Run
TC-171 | Verify behaviour on direct navigation to a non-existent URL | P3 | Negative Flows | Manual | Not Run
TC-180 | Verify smoke suite passes on Firefox | P1 | Compatibility | Regression | Not Run
TC-181 | Verify smoke suite passes on Safari | P1 | Compatibility | Manual | Not Run
TC-190 | Verify Home page initial load < 3 seconds on standard broadband | P1 | Performance | Manual | Not Run
TC-191 | Verify navigation between pages < 1 second | P2 | Performance | Manual | Not Run
TC-192 | Verify Add to Basket response < 100ms | P2 | Performance | Manual | Not Run
TC-193 | Verify Lighthouse Performance score on Home page | P2 | Performance | Manual | Not Run
TC-194 | Verify Lighthouse Performance score on /sweets page | P2 | Performance | Manual | Not Run
TC-195 | Verify pages render under Slow 3G throttle | P3 | Performance | Manual | Not Run
TC-196 | Verify GIF banner asset size and loading approach | P3 | Performance | Manual | Not Run
TC-197 | Verify /sweets product image loading does not block page interactivity | P2 | Performance | Manual | Not Run
TC-200 | Verify XSS injection in text fields is treated as plain text (parameterised) | P1 | Security | Manual | Not Run
TC-201 | Verify XSS injection on Login fields | P1 | Security | Manual | Not Run
TC-202 | Verify zero network requests on Continue to checkout (no card data on the wire) | P0 | Security | Manual | Not Run
TC-203 | Verify no card data is logged to browser console | P1 | Security | Manual | Not Run
TC-204 | Verify HTTPS is used and no mixed content warnings | P2 | Security | Manual | Not Run
TC-205 | Verify no third-party tracking or analytics loaded | P3 | Security | Manual | Not Run
TC-206 | Verify direct URL access does not bypass any expected access control | P3 | Security | Manual | Not Run
TC-207 | Verify card data is not stored in browser autofill memory after submission | P2 | Security | Manual | Not Run
TC-208 | Verify form action attribute does not leak to a real endpoint | P1 | Security | Manual | Not Run
TC-210 | Verify all product images have descriptive alt text | P2 | Accessibility | Manual | Not Run
TC-211 | Verify all form inputs are associated with visible labels | P2 | Accessibility | Manual | Not Run
TC-212 | Verify error messages are programmatically associated with their fields | P2 | Accessibility | Manual | Not Run
TC-213 | Verify Lighthouse Accessibility audit on key pages | P2 | Accessibility | Manual | Not Run
TC-214 | Verify keyboard navigation through forms | P3 | Accessibility | Manual | Not Run
TC-215 | Verify color contrast on primary text and error messages | P3 | Accessibility | Manual | Not Run
TC-216 | Verify focus indicator is visible on all interactive elements | P3 | Accessibility | Manual | Not Run
TC-217 | Verify basket count change is announceable to screen readers | P3 | Accessibility | Manual | Not Run
TC-220 | Verify no critical JS errors on initial load of any page | P1 | DevTools | Manual | Not Run
TC-221 | Verify Network tab shows expected static asset loads only | P3 | DevTools | Manual | Not Run
TC-222 | Verify Sources tab exposes basket logic and price calculation functions | P3 | DevTools | Manual | Not Run
TC-223 | Verify Application Storage panel shows basket key after items added | P3 | DevTools | Manual | Not Run
TC-230 | Verify KI register matches Spec §17 — full pass | P3 | Known Issues | Manual | Not Run
TC-240 | Verify behaviour at 200% browser zoom | P3 | Cross-cutting | Manual | Not Run
TC-241 | Verify behaviour at narrow viewport (1024px wide) | P3 | Cross-cutting | Manual | Not Run
TC-242 | Verify text selection and copy behaviour on page content | P3 | Cross-cutting | Manual | Not Run
TC-243 | Verify URL behaviour on hash change and query string | P3 | Cross-cutting | Manual | Not Run
TC-244 | Verify behaviour in incognito / private browsing mode | P3 | Cross-cutting | Manual | Not Run
TC-245 | Verify favicon loads on all pages | P3 | Cross-cutting | Manual | Not Run

## Coverage Summary
Coverage Summary Dashboard
Requirements Coverage
Metric | Count | Percentage
Total Requirements (FR + NFR) | 26 | 100.0%
Functional Requirements (FR-01..18) | 18 | 69.23%
Non-Functional Requirements (NFR-01..08) | 8 | 30.77%
Requirements with at least 1 test case (Covered) | 26 | 100%
Requirements with NO test case (GAP) | 0 | 0%
Test Case Distribution
Bucket | Count | Percentage
Total Test Cases | 158 | 100.0%
P0 — Critical | 20 | 12.66%
P1 — High | 41 | 25.95%
P2 — Medium | 53 | 33.54%
P3 — Low | 44 | 27.85%
Smoke (PR-level CI) | 8 | 5.063%
Regression (merge + nightly) | 69 | 43.67%
Manual only | 81 | 51.27%
Execution Status (live from Execution Log)
Status | Count | % of Total
Not Run | 158 | 100%
Pass | 0 | 0%
Fail | 0 | 0%
Blocked | 0 | 0%
Skipped | 0 | 0%

## Defect Anchor
Defect Anchor
As defects are raised during execution, log them here AND populate the Defect ID column on the Execution Log sheet for the failed test case. The RTM (Forward) sheet will automatically aggregate defect IDs against the affected requirements.
Defect ID | Title | Severity | Priority | Status | Test Case ID | Requirement | Date Raised | Owner | Notes

## Legend
Legend & Definitions
Priority
Value | Definition
P0 | Critical — must pass at exit; covers core flows and key calculations
P1 | High — should pass at exit; covers important features and validations
P2 | Medium — should be executed; covers secondary features
P3 | Low — nice to execute; covers edge cases and cosmetic checks
Automation
Value | Definition
Smoke | Runs on every PR via CI; build rejected if any fails
Regression | Runs on merge to main and nightly; full automated suite
Manual | Manual execution only — exploratory, DevTools-driven, or visual
Status (Execution Log)
Value | Definition
Not Run | Case has not yet been executed
Pass | All PASS conditions verified
Fail | A FAIL condition was observed; raise defect and record Defect ID
Blocked | Case cannot be executed due to environment, build, or dependency issue
Skipped | Case intentionally excluded for this run (with reason in Notes)
Coverage Status (RTM Forward)
Value | Definition
Covered | Requirement has at least one test case mapped to it
GAP | Requirement has NO test case — must be addressed before execution begins
Defect Severity (Defect Anchor)
Value | Definition
Critical | Core flow blocked; no workaround
High | Major function broken; workaround exists or feature partially works
Medium | Minor function broken; cosmetic with usability impact
Low | Cosmetic or trivial; no usability impact
Defect Priority (Defect Anchor)
Value | Definition
P1 | Fix now — block exit
P2 | Fix this cycle — should be fixed before exit
P3 | Fix soon — should be fixed in the next cycle
P4 | Fix eventually — backlog; nice-to-have